Field Officer Handbook

Retail outlet census · Six-day routine, interactions and fallbacks

| Field | Detail |
| --- | --- |
| Issued to | Willys Munyanga, Nelius, Evans Mutune, Erick Kyalo, Peter Owuor |
| Programme | Market Link — retail outlet census for Nice Millers Ltd |
| Engagement Lead | Laban Mwangi |
| Version | Field Officer Handbook v1.0 — 13 August 2026 |
| Read with | Your individual Field Officer Sheet, which carries your area, your lead and your targets |

# 1. What the job actually is

You are building a register of every shop that sells flour across Nairobi, Kiambu and the Kajiado towns. Not a rough list — a verified record of each one, with its exact location, who runs it, what it stocks, and how much it moves.

Two things follow from that, and they shape everything else in this handbook.

- You are not selling. You take nothing, offer nothing, and promise nothing. The moment a shopkeeper thinks you are selling, the conversation changes and the data gets worse.

- A wrong record is worse than a missing one. A shop you did not reach is a gap we can see and fix. A shop you guessed at is invisible, and it corrupts everything built on top of it.

Your engagement: paid on a daily rate, starting on probation, with a view to permanent. What moves you from probation to permanent is not how many outlets you count — it is whether your records hold up when your lead spot-checks them.

# 2. The six-day week

All six days are coverage days, Monday to Saturday. There is no separate review day — the review is folded into the end of each day, and Saturday absorbs the week’s revisits. Sunday is off.

| Day | Mode | What it is |
| --- | --- | --- |
| Monday | Coverage | Your lead posts the week’s map and your daily targets by 07:15. Fresh area, full day. |
| Tuesday | Coverage | Standard route day. |
| Wednesday | Coverage | Duplicate and quality flags land in the evening. Clear yours before you close. |
| Thursday | Coverage | Standard route day. |
| Friday | Coverage | Standard route day. File your weekly notes in the evening review. |
| Saturday | Coverage | Market-day areas and the week’s revisits — every shop that was closed or refused Monday to Friday. |
| Sunday | Rest | No field work, no sync, no group traffic. |

## The day itself

| Time | Block | Detail |
| --- | --- | --- |
| 06:45 | Kit check | Phone charged past 90%, power bank packed, paper forms as backup, ID and vest on. Do this at home, not at the first shop. |
| 07:15 | Morning brief | Fifteen minutes. Your lead gives the area, the split between you and your partner, and your count target. |
| 07:45 – 13:00 | Block A | 18 to 22 outlets. One side of the street out, the other side back. Pin every outlet while standing in front of it. |
| 13:00 – 13:45 | Break and midday count | Eat, and post your running count to the cluster group. If you are behind, say it now. |
| 13:45 – 17:15 | Block B | 10 to 14 outlets. Keep the last hour for shops that were closed or busy in the morning. |
| 17:15 – 18:00 | Evening review | Sync everything. Fix any flagged record. Log revisits. File your report: captured, closed, refused, synced, anything unusual. |
| 18:00 | Close | Everything synced. No backlog past 24 hours. |

On the evening review: this is the part of the six-day week that people quietly skip, and it is the part that makes the six-day week work at all. Forty-five minutes at the end of the day replaces a whole day off the field. Skip it for three days running and your lead is clearing your flags instead of running the cluster.

# 3. Your numbers

| Line | Value |
| --- | --- |
| Target per day | 30 outlets — working band 20 to 40 |
| Coverage days per week | 6 (Monday to Saturday) |
| Coverage days per wave | 24 (4 weeks) |
| Your target per wave | 720 outlets |
| Your programme total | 1,440 outlets across both waves |
| Cluster total (you and your lead) | 2,880 outlets |
| Programme gross | 14,400 outlets |
| Programme net after duplicates, closures and refusals | ≈ 12,200 verified outlets |
| Contracted commitment | 10,000+ |

What the six-day week bought: under the old five-day plan there were 20 coverage days per wave and the margin over the 10,000 commitment was about 2% — one bad week and the programme missed. Six-day weeks give 24 coverage days in four weeks instead of five, which shortens the field programme from ten weeks to eight and lifts the margin to roughly 20%. That margin is the point. It is not a reason to relax the daily target; it is what stops one bad week from sinking the whole thing.

# 4. At the outlet

Eight fields, every time. A record missing any of them is incomplete.

| Field | What it means |
| --- | --- |
| Location | GPS pin captured while standing at the door |
| Identity | Shop name and type — duka, kiosk, mini-market, supermarket, wholesaler, eatery, posho mill |
| Contact | Owner or manager name and a working phone number |
| Proof | Shopfront photo with the signage legible |
| Shelf | Flour brands stocked and how many facings each holds — Nice, Unga, Pembe, Capwell, other |
| Volume | Monthly offtake in bales |
| Supply | Who supplies them — distributor, wholesaler, or direct |
| Landmark | Nearest landmark, street or estate name, written out |

Two rules void a record: no pin, no record; no photo, no record. Neither counts toward your daily total. This is not bureaucracy — a record nobody can verify is worth nothing to the client and nothing to us.

# 5. How to handle the interaction

## Opening

Greet first, in whatever language they greet you in. Then your name, then Market Link, then what you are doing and how long it takes. Give them a way to say no — people who feel cornered refuse, and people asked properly usually agree.

“Habari yako. My name is ___, I work with Market Link. We are mapping shops in this area so suppliers can serve you better. It takes about three minutes — is now okay, or should I come back?”

If they say come back, write down when and actually come back. A kept promise is why the second half of your week goes better than the first.

## Always

- Wait if they are serving a customer. Never interrupt a sale — it is the fastest way to be thrown out of a shop.

- Ask before you photograph. Every time, not just the first time.

- Carry your ID and wear the vest. People relax when they can see who you are.

- Keep it to three or four minutes unless they want to talk. Respecting their time is what gets you the next shop.

- Say thank you and leave well, whether they helped or not. Someone will come back here.

## Never

- Never promise supply, stock, credit, a distributor visit or a better price. You are not selling and you cannot commit anyone. A promise you cannot keep costs the company a relationship.

- Never criticise Unga, Pembe, Capwell or any brand in front of an owner. You are counting, not campaigning.

- Never argue — about price, politics, or anything else. Record what they say and move on.

- Never ask for or accept money, goods or a discount from a shop. Not even a soda. It changes what you are.

- Never enter a back room, store or house. Do your work at the counter.

- Never invent a record. Spot-checks are daily and duplicates are flagged twice a week. It will be found, and it is the one thing that ends an engagement immediately.

# 6. Fallbacks

Fourteen situations that will happen. Knowing the answer in advance is the difference between losing ten minutes and losing an afternoon.

| Situation | What you do |
| --- | --- |
| Shop is closed | Log it as closed with the time. Never skip silently. It goes on Saturday’s revisit list. |
| Owner away, attendant present | Capture what the attendant can answer, mark the record attendant-sourced, flag it for revisit. |
| They refuse | Log the refusal and the reason if offered. Thank them, move on. Never push. |
| Crowd forming, or someone hostile | Leave immediately and call your lead. Do not finish the record first. |
| Asked if you are government or police | Show your ID. Say you work for Market Link, a private company mapping shops for suppliers. Offer your lead’s number. |
| Police or county askari stop you | Stay calm, do not argue, do not pay anything. Call Laban immediately. |
| Phone dies | Switch to the paper form and keep working. Enter everything the same evening. |
| No network | Keep capturing offline. Sync when signal returns or at the end of the day. Never wait for tomorrow. |
| GPS will not lock | Step into the open, wait thirty seconds. If it still fails, record landmark and street clearly, flag it, tell your lead. |
| Behind target at midday | Say so at the 13:00 count. Your lead can move the split. Discovering it at 17:00 is too late. |
| Sick or unable to work | Tell your lead before 07:00, not at 09:00. |
| Phone lost or stolen | Report the same day to your lead and to Ian. It holds shop data — that matters more than the handset. |
| Asked to work outside your area | Do not. Call your lead first. Freelancing creates duplicates and wrecks the count. |
| Wholesaler or big retailer wants to talk business | Take their name and number, say someone will call, pass it to your lead the same day. Negotiate nothing yourself. |

# 7. Escalation

| How fast | What | To whom |
| --- | --- | --- |
| Now | Anything unsafe or hostile, or involving police | Lead, then Laban |
| Same day | Phone, app or sync failure; lost or stolen device | Lead, then Ian |
| Same day | Running more than 15% below target | Lead |
| Before acting | Any request to work outside your cluster | Lead |
| 24 hours | A commercial lead from a wholesaler or retailer | Lead, then Laban |
| Before 07:00 | Illness or any day you cannot work | Lead |

# 8. Two honest cautions

## On the six-day week

Six days of walking, week after week, is genuinely hard, and the programme is asking for eight of them. Weeks four and five are where people start missing counts and getting careless without noticing it themselves. If you are exhausted, say so early to your lead. A planned lighter Saturday costs the programme almost nothing. Someone quitting in week five costs it a great deal, and it costs you more.

## On safety

Nothing in this handbook — no target, no count, no deadline — is worth your safety. If an area feels wrong, leave it and call your lead. You will not be blamed for stopping. You would be blamed for pushing on.

Market Link is a Playmax project. Everything you record belongs to Playmax and is confidential. Do not share shop data, photographs or lists outside the programme systems.